Sector Support Fund

England’s Creative Coast – The coastline of Essex, Kent and Sussex is home to some of the UK’s most distinctive galleries and art events. This project will build on and celebrates this success. The coastal arts organisations are working together for the first time that will connect art with the coastline to explore its ecology, history and future, and visitors are invited to explore the region in a new way. During 2019 the group worked on a series of art commissions and creative initiatives that will connect the coastline of Essex, Kent and East Sussex. The artworks are planned to be unveiled in Spring 2021 (note: this has now been postponed until Spring 2021, due to Covid-19). Group – South East Creative Economy Network (SECEN); SSF award £150,000; Total project costs £1,179,000

Good Food Growth– This project was allocated funding in 2018/19, but ran through 2019, finishing in March 2020. The aimed to support growers, processors, retailers, food businesses and new entrants to raise awareness of the opportunities available within the food and drink sector to develop and enhance their businesses thereby adding both volume and value to the sector. The project met its target of 3 scoping workshops being held, this was followed by 3 training workshops (one in each area), meet the buyer events were held in Sussex, Kent and Essex and 4 management team meeting were held. Unfortunately, the final conference which was due to be held in March 2020 was cancelled due to the Covid-19 outbreak. Group – Rural; SSF award £96,000; Total project cost £151,500

Energy and Clean Growth (Supply Chain Mapping) – hasn’t started yet but received funding in 2019. This project will take an in-depth analysis of the supply chain for the local energy and clean growth sector and will refresh and build upon the now out of date analysis of the Low Carbon Environmental Goods and Services sector that was undertaken in 2012. The project was allocated funding in 2019/20 but Covid-19 happened before it could get started, so the project will recommence during the summer of 2020. Group – Clean Growth; SSF award £129,500; Total project cost £185,000

Future Proof? – I have asked Jemma Little for a copy of the final report which they had said would be made available for the SELEP website. Group – Housing; SSF award £110,000; Total project cost £157,425

Note: Two projects were allocated Sector Support Funding in 2019/20