## Summary
Appendix B - GBF Pipeline Assessment Spreadsheet
Getting Building Fund - applications for additional funding
Summary
Project name and brief description (max 50 words) | Federated Area | Federated Area priority ranking | Existing GBF allocation | Amount of GBF spent to date | % of GBF allocation spent to date | Actual/ expected completion date for full spend of original GBF funding allocation | Amount of GBF funding committed to date | % of GBF allocation committed to date | Additional GBF requested | Purpose of GBF funding sought? | Strength of case for requesting additional GBF funding Formula - please do not edit cell | Change in project benefits since original Business Case submission Formula - please do not edit cell | Estimated value for money of project Formula - please do not edit cell | Can the project proceed without additional GBF funding? Relates to projects seeking funding to deliver original Business Case only Formula - please do not edit cell | Remaining risks | Remaining barriers to project delivery Formula - please do not edit cell | Comments
Thanet Parkway Railway Station - A new railway station on the Ashford International – Ramsgate railway line at Cliffsend with associated level crossing/signalling upgrades to improve accessibility to rail in Thanet, which is a historically economically disadvantaged part of the county. | KMEP | 1 | 11999000 | 11999000 | 100% | 2022-03-01 | 11999000 | 100% | 875000 | To support delivery of original Business Case | Strong | Project benefits unchanged | Expected to remain comfortably above 2:1 | Yes, but potentially with an adverse impact on project completion date | Total project cost unknown presenting risk to BCR but project currently offers Very High value for money | Yes - there are remaining barriers to project delivery which may impact on completion date | S151 Sign Off received Application Form Also received LGF funding No real additionality/unable to confirm the total project cost
Innovation Park Medway - Sustainable City of Business - delivery of one section of 'The Runway Park' on the northern site of Innovation Park Medway. The Runway Park will be a primary forum for collaboration, bringing businesses and individuals together to foster an innovative spirit, and enable businesses to interact with the wider community. | KMEP | 2 | 778323 | 778323 | 100% | 2022-03-01 | 778323 | 100% | 400000 | To support delivery of original Business Case | Strong | Project benefits unchanged | Expected to remain comfortably above 2:1 | Yes, but with an adverse impact on the project outputs and outcomes | Risk of reduced demand (mitigated through provision of demand study) | No - there are no remaining barriers to project delivery | S151 Sign Off received Application Form Also received LGF, SSF and GPF funding
Javelin Way Development - Delivery of light industrial units which act as an enabling development in order to deliver the Jasmin Vardimon Dance Laboratory in Ashford. | KMEP | 3 | 578724 | 578724 | 100% | 2021-03-01 | 578724 | 100% | 235728 | To support delivery of original Business Case | Medium | Project benefits unchanged | Expected to remain comfortably above 2:1 | Yes, but with an adverse impact on the project outputs and outcomes | Utility works required | No - there are no remaining barriers to project delivery | S151 Sign Off received Application Form Also received GPF funding Need to confirm request with Sarah - application form states £235,728. KMEP prioritisation states £235,724
Techfort Phase 2, The Citadel, Dover - refurbishment of Casemates 53 and 54 to accommodate a unique mix of cultural uses, small businesses and craft workshops. | KMEP | 4 | 1009000 | 0 | 0% | 2022-12-01 | 1009000 | 100% | 850000 | To enable delivery of an extension to the existing project | Medium | N/A - new Business Case | Expected to remain comfortably above 2:1 | N/A - new Business Case | Conditions attached to Planning Consent and Scheduled Monument Consent need to be released | Yes - there are remaining barriers to project delivery which may impact on completion date | S151 Sign Off received. Extension to GBF spend approved to December 2022 Business Case - Gate 1 review undertaken by Steer. Conclusion - Business Case is generally strong but further clarification is needed in relation to some aspects of the Economic Case. Inter-gate meeting to be held if project prioritised. Spend to date taken from most recent KCC GBF quarterly reporting submission. Need to confirm with Kerry as to whether the original GBF funding allocation has been committed through entering into a construction contract | KMEP
Discovery Park Incubator - Delivery of new incubator, self contained laboratory units, informal break out area and shared lab support facilities in Building 500 at Discovery Park | KMEP | 5 | 2500000 | 1434000 | 57.36% | 2022-09-30 | 2500000 | 100% | 250000 | To support delivery of original Business Case | Medium | Project benefits unchanged | Expected to remain comfortably above 2:1 | Yes, but with an adverse impact on the project outputs and outcomes | Potential for extended lead in times for specialist lab equipment | No - there are no remaining barriers to project delivery | S151 Sign Off received Extension to GBF spend to March 2023 approved Application Form Need to confirm with Kerry re GBF spend to date. How much funding has been issued to Discovery Park by KCC - £891,000 or £1,434,000? | OSE
Extension of the existing Phase 2 ASELA LFFN project - GBF funding has been requested to extend the LFFN project into Phase 3 allowing more areas in South Essex to benefit from the roll-out of full fibre infrastructure. | OSE | 1 | 2500000 | 2500000 | 100% | 2022-09-01 | 2500000 | 100% | 500000 | To enable delivery of an extension to the existing project | Medium | N/A - new Business Case | Unknown - Value for Money exemption applied | N/A - new Business Case | Project delivery will rely on established governance processes used for the original phase of the project | No - there are no remaining barriers to project delivery | S151 Sign Off received from Southend on Sea City Council as Accountable Body for ASELA but not Thurrock Council. Business Case - ITE still to undertake initial review of Business Case. Need to confirm that full spend of initial GBF funding allocation has been achieved. | Success Essex
Tindal Square, Chelmsford - creation of a new civic public square of over 3,000 sqm that provides a destination space for arts, events and celebrations outside Shire Hall in Chelmsford City Centre. | Success Essex | 1 | 750000 | 750000 | 100% | 2022-03-01 | 750000 | 100% | 450000 | To support delivery of original Business Case | Strong | Project benefits unchanged | Unknown - Value for Money exemption applied | Yes, but with an adverse impact on the project outputs and outcomes | No risks to project delivery identified | No - there are no remaining barriers to project delivery | S151 Sign Off received from Chelmsford City Council but not ECC. ECC Sign Off needed. Application form. | TES
Extension of the full-fibre broadband rollout in Essex to reach rural and hard to reach premises - Superfast Essex is a broadband improvement programme run by Essex County Council. The programme aims to make superfast and ultrafast broadband available to as many homes and businesses across Essex as possible. GBF funding extended the Superfast Essex Phase 4b rollout programme to reach additional rural areas. | Success Essex | 2 | 1820000 | 270109.61 | 14.84% | 2023-03-01 | 1820000 | 100% | 477256 | To support delivery of original Business Case | Strong | Project benefits unchanged | Expected to remain comfortably above 2:1 | Yes, but with an adverse impact on the project outputs and outcomes | Mitigation measures in place for all identified risks | No - there are no remaining barriers to project delivery | S151 Sign Off not received Application form Confirm GBF spend to date with Paul - has the £53,103.30 detailed on the application form as spent but unclaimed now been claimed? Confirm with Paul that full GBF funding allocation is committed. Application form slightly confusing but appears to reflect unspent balance as committed.
Jaywick Market and Commercial Space - the project includes the build of a covered market and affordable business space on a gateway site in Jaywick Sands to support the local economy, grow local entrepreneurship, and grow and retain economic activity and job creation in the local area, which is the most deprived in the country. | Success Essex | 3 | 1972000 | 747495.25 | 37.91% | 2022-12-01 | 1972000 | 100% | 419060 | To support delivery of original Business Case | Strong | Project benefits increased | Expected to remain comfortably above 2:1 | Yes, but with an adverse impact on the project outputs and outcomes | Ongoing risk of further contamination or ground obstructions in the area surrounding the building - leading to uncertainty as to total project cost and impact on BCR | No - there are no remaining barriers to project delivery | Letter from Tendring DC Chief Exec received but ECC S151 Sign Off still required. Application form. | Cannot proceed without additional funding being confirmed
Enterprise Centre for Horizon 120 Business and Innovation Park - delivery of a new 3,100 sqm Enterprise Centre building with a variety of office spaces. There will also be a flexible conference space that can be transformed into smaller units. It is a purpose built physical and virtual environment designed to drive collaboration, encourage idea generation and underpin problem solving. | Success Essex | 4 | 7000000 | 7000000 | 100% | 2022-03-01 | 7000000 | 100% | 907124 | To support delivery of original Business Case | Medium | Project benefits unchanged | Expected to remain comfortably above 2:1 | Original GBF project can be delivered without additional funding but extra funding would allow realisation of additional outputs/outcomes | No risks to project delivery identified | No - there are no remaining barriers to project delivery | S151 Sign Off received from Braintree District Council but not from ECC. ECC sign off needed. Application form. Need to read through in more detail to confirm that this is definitely to support delivery of works outlined in the original Business Case. | Yes, but with an adverse impact on the project outputs and outcomes
Tendring Bikes and Cycle Infrastructure - the project will deliver a bespoke bike scheme and cycle network infrastructure within Jaywick Sands and Clacton aimed at tackling inequality within one of the most deprived areas of the country. | Success Essex | 5 | 2300000 | 518887 | 22.56% | 2023-03-01 | 2300000 | 100% | 300200 | To support delivery of original Business Case | Weak | Project benefits increased | Expected to be around 2:1 | Original GBF project can be delivered without additional funding but extra funding would allow realisation of additional outputs/outcomes | Extended lead in times and increasing costs - mitigation measures have been identified for all risks | No - there are no remaining barriers to project delivery | S151 Sign Off required Application form Need to confirm with Paul the amount of additional GBF funding sought - application forms states £300,200 but Success Essex prioritisation states £300,000 | Yes, but potentially with an adverse impact on project completion date
Restoring the Glory of the Winter Garden - Phase 2 - Establishment of a new facility, Racquet Studios, in the Winter Garden. Racquet Studios would be a world class facility for virtual film production, a centre of excellence for skills training in digital and creative arts and a leading virtual film production research and development facility. | TES | 1 | 1600000 | 1600000 | 100% | 2022-03-01 | 1600000 | 100% | 900000 | To enable delivery of an extension to the existing project | Strong | N/A - new Business Case | Value for Money exemption applied | N/A - new Business Case | Risk of increasing costs which may impact project delivery. Risk that the project may not be affordable in the long-term | Yes - there are remaining barriers to project delivery which may prevent project completion | S151 Sign Off received from Eastbourne BC but not ESCC. ESCC sign off needed. Business Case - Gate 1 review undertaken by Steer. Conclusion - Business Case is reasonably strong but further clarification needed on a number of items including Economic Case and completion of M&E templates still required. | Original GBF project can be delivered without additional funding but extra funding would allow realisation of additional outputs/outcomes
Seven Sisters Country Park Visitor Infrastructure Uplift - the project delivers a comprehensive refresh of the visitor offer at the Country Park, including 233 sqm of new retail space for local businesses and accommodation for the Site Warden. | TES | 2 | 200000 | 54840 | 27.42% | 2022-09-01 | 200000 | 100% | 84100 | To support delivery of original Business Case | Strong | Project benefits unchanged | Unknown - Value for Money exemption applied | Yes, but with an adverse impact on the project outputs and outcomes | Listed Building Consent required - identified as Barrier to Delivery | Yes - there are remaining barriers to project delivery which may prevent project completion | S151 Sign Off still required Application Form | N/A - new Business Case
Observer Building, Hastings - the project will support the full redevelopment of the 4,000 sqm Observer Building, which has been empty and increasingly derelict for 35 years, into a highly productive mixed-use building, creating new homes, jobs, enterprise space and support. | TES | 3 | 1713000 | 1713000 | 100% | 2022-03-01 | 1713000 | 100% | 315000 | To support delivery of original Business Case | Medium | Project benefits unchanged | Expected to remain comfortably above 2:1 | Yes, but with an adverse impact on the project outputs and outcomes | Potential for further cost increases as current costs only held for a short period | No - there are no remaining barriers to project delivery | S151 Sign Off still required Application Form Also received GPF funding Application form seeks additional funding of £650,000. Need to confirm with Alex that he is happy for me to take forward the smaller value shown in the TES prioritisation - presents less of a VfM risk
Accessing Charleston: Removing the Barrier to Growth (project extension) - establishing a low carbon way for visitors to access Charleston through provision of electric vehicle charging points in the car park and purchase of a electric minibus to convey people to the site from rail and bus stations. | TES | 4 | 329835 | 329835 | 100% | 2021-09-01 | 329835 | 100% | 321414 | To enable delivery of an extension to the existing project | Weak | N/A - new Business Case | Unknown - Value for Money exemption applied | N/A - new Business Case | Fast moving nature of the Electric Vehicle market may affect long-term viability of project. Risk of long lead-in times for Electric Vehicles and Electric Vehicle charging infrastructure | Yes - there are remaining barriers to project delivery which may prevent project completion | S151 Sign Off still required Business Case. Gate 1 review undertaken by Steer. Conclusion - insufficient information provided to be able to assure value for money. Further information required to strengthen each case of the Business Case. Also received GPF funding for other improvements to the Charleston site. Balance remains outstanding.
Sussex Innovation, Falmer - COVID secure adaptions (Hybrid Working Enhancements) - further development on the site to enable more effective hybrid working, including investment in technology (laptops and server upgrade), building enhancements, enhanced hygiene facilities and sustainable transport investment. | TES | 4 | 200000 | 200000 | 100% | 2021-09-01 | 200000 | 100% | 200000 | To enable delivery of an extension to the existing project | Weak | N/A - new Business Case | Unknown - Value for Money exemption applied | N/A - new Business Case | Risk of extended lead in time for technological equipment required | No - there are no remaining barriers to project delivery | S151 Sign Off still required Business Case. Gate 1 review undertaken by Steer. Conclusion - insufficient information provided to be able to assure value for money. Further information required to strengthen each case of the Business Case.
Yes - there are remaining barriers to project delivery which may prevent project completion
No - there are no remaining barriers to project delivery
Yes - there are remaining barriers to project delivery which may impact on completion date
Value for Money exemption applied
Expected to remain comfortably above 2:1
Expected to be around 2:1
Expected to fall below 2:1
Unknown - Value for Money exemption applied
Unknown - not calculated
Project benefits increased
Project benefits unchanged
Project benefits reduced
N/A - new Business Case
Strong
Medium
Weak
To support delivery of original Business Case
To enable delivery of an extension to the existing project
Yes, GBF funding will be spent in full by 31 December 2022
Yes, GBF funding will be spent in full by 31 March 2023
No, GBF funding cannot be spent in full by 31 March 2023

## Case for additional funding
Getting Building Fund - applications for additional funding
Case for additional funding
Project name and brief description (max 50 words) Formula - please do not edit cell | Federated Area Formula - please do not edit cell | Additional GBF requested Formula - please do not edit cell | If additional funding is awarded, will it be possible for the funding to be spent in full by 31 March 2023? | Why is additional GBF funding required? To include consideration of the impact of COVID-19, Brexit or High Inflation Levels on the project (where funding is sought to support delivery of existing Business Case) | What are the implications for the project and its' ability to deliver in accordance with the Business Case, if additional funding is not awarded? (where funding is sought to support delivery of existing Business Case) | For extensions to existing projects - if GBF funding is not awarded, what are the implications for the proposed works? Consideration should be given as to whether it will still be possible to bring the works forward and the likely timetable for this. | Strength of case for requesting additional GBF funding | Comments
Thanet Parkway Railway Station - A new railway station on the Ashford International – Ramsgate railway line at Cliffsend with associated level crossing/signalling upgrades to improve accessibility to rail in Thanet, which is a historically economically disadvantaged part of the county. | KMEP | 875000 | Yes, GBF funding will be spent in full by 31 March 2023 | The project has experienced a number of cost increases due to: • Materials cost increases • Additional costs associated with ensuring safe working practices during the COVID-19 pandemic • The need to implement alternative solutions as an interim measure due to significantly extended lead-in times for microchips • Design-led changes driven by the rail industry and safety considerations • Increased costs associated with the required level crossing works. Initial cost increases were met by Kent County Council but additional GBF funding is now required to safeguard the level crossing works which need to be completed before the station can open. | Project specific - without additional GBF funding there is a risk that it will not be possible for the level crossing works to be taken forward and this would prevent the station from opening. Wider implication - financial contribution required from Kent County Council has been greater than forecast which has implications for their capital and revenue provision elsewhere. | N/A | Strong | Quarterly GBF spend profile required to be clear if funding can be spent in full by December 2022 or March 2023.
Innovation Park Medway - Sustainable City of Business - delivery of one section of 'The Runway Park' on the northern site of Innovation Park Medway. The Runway Park will be a primary forum for collaboration, bringing businesses and individuals together to foster an innovative spirit, and enable businesses to interact with the wider community. | KMEP | 400000 | Yes, GBF funding will be spent in full by 31 March 2023 | Additional GBF funding is required due to: • increasing materials costs due to the impacts of the COVID-19 pandemic and due to rising inflation levels • the need for COVID safe construction practices which extended the delivery programme • supply chain issues including extended lead-in times for certain materials. Further compounded by Brexit and associated labour shortages. | If additional GBF funding is not awarded, there are elements within the original project scope which would need to be reviewed, including consideration of use of alternative materials. Use of alternative materials would threaten the quality of IPM as set out in the Design Code and LDO. Any elements removed from the project could potentially be delivered at a later date but the cost would be significantly higher. If additional GBF funding is not awarded, delivery of the works could be delayed as self-certification for use of other materials is sought under the LDO. | N/A | Strong | Strong case for investment but would need written commitment from Medway with regard to submission of quarterly reporting if additional funding was to be awarded.
Javelin Way Development - Delivery of light industrial units which act as an enabling development in order to deliver the Jasmin Vardimon Dance Laboratory in Ashford. | KMEP | 235728 | Yes, GBF funding will be spent in full by 31 December 2022 | Additional GBF funding is required due to: • increased costs associated with ensuring a safe working environment during the COVID-19 pandemic • inflated materials costs including a 36% increase in the cost of windows and a 56% increase in the cost of pre-cast concrete • extended delivery programme due to delays in receiving required materials from outside the UK due to border delays at customs. | Without additional funding, the project will still be delivered as additional funding has been provided by Kent County Council, however, the quality of the fit out will be reduced and some elements of the project, such as solar panels, will not be delivered. Without additional funding, the project may not breakeven. In addition, the increased financial commitment required from Kent County Council will place pressure on their overall budget. | N/A | Medium | Medium strength - project will be delivered anyway but with some value engineering. KCC have bridged the immediate funding gap.
Techfort Phase 2, The Citadel, Dover - refurbishment of Casemates 53 and 54 to accommodate a unique mix of cultural uses, small businesses and craft workshops. | KMEP | 850000 | Yes, GBF funding will be spent in full by 31 March 2023 | N/A | N/A | If GBF funding is not awarded to support delivery of the project, it is likely that the works will not be forthcoming in the short-term. This will lead to a further deterioration of the ancient monument with intrusion, graffiti and degradation likely to have a negative impact. | Medium | Programme indicates that 4 months is needed for the refurbishment work. No dates have been applied but there is a risk that funding will not be spent by 31 March 2023. Medium case for investment due to programme risk
Discovery Park Incubator - Delivery of new incubator, self contained laboratory units, informal break out area and shared lab support facilities in Building 500 at Discovery Park | KMEP | 250000 | Yes, GBF funding will be spent in full by 31 March 2023 | Additional GBF funding is required due to increases in materials and labour rates due to inflation. Work has been undertaken to identify potential savings and to mitigate against cost overruns but there remains a funding gap if the project is to be completed. | If additional funding is not awarded, it may result in some of the breakout areas and shared laboratory facilities not being completed. | N/A | Medium
Extension of the existing Phase 2 ASELA LFFN project - GBF funding has been requested to extend the LFFN project into Phase 3 allowing more areas in South Essex to benefit from the roll-out of full fibre infrastructure. | OSE | 500000 | Yes, GBF funding will be spent in full by 31 March 2023 | N/A | N/A | If GBF funding is not awarded to support delivery of the project, progress towards provision of full fibre across the whole region will be severely impacted. This will have a detrimental impact on the Government's drive to stimulate the economy post COVID. Businesses and communities will be put at a disadvantage with a consequent impact on future opportunities, growth and well-being. It is acknowledged that the need for improved connectivity will eventually be addressed by the market but there is a risk that areas of the South Essex region will be left behind in the meantime. There is no indication in the Business Case that alternative funding sources are available to deliver this work. | Medium | Need clarity on the situation around Thurrock with regard to securing S151 sign off and whether there are issues with awarding additional funding. Case for funding flagged as Medium due to significant weaknesses in the Business Case but am still awaiting outcome of ITE review. Additional info needed on risks, VfM, benefits, additionality.
Tindal Square, Chelmsford - creation of a new civic public square of over 3,000 sqm that provides a destination space for arts, events and celebrations outside Shire Hall in Chelmsford City Centre. | Success Essex | 450000 | Yes, GBF funding will be spent in full by 31 March 2023 | Additional GBF funding is required due to the following reasons: • Scope within the construction contract for elements of inflated costs to be passed onto the client including increase in fuel prices, increase in site compound costs and 10 to 15% increase in materials costs. • Brexit related impacts including longer than expected lead in times for materials/equipment being imported from EU countries and workforce depletion within utilities companies resulting in delays to the project as emergency works are prioritised • COVID-19 impacts including delays to worldwide materials supplies due to ongoing lockdowns and additional measures needed to protect the workforce from COVID-19 | If additional funding is not awarded, it will not be possible for the full scope of the project, as detailed in the approved Business Case, to be delivered due to the cost increases experienced. The additional funding will ensure that the full public realm improvement scheme can be delivered. | N/A | Strong | Can any more information be provided as to what would be removed from the project scope if additional funding was not secured?
Extension of the full-fibre broadband rollout in Essex to reach rural and hard to reach premises - Superfast Essex is a broadband improvement programme run by Essex County Council. The programme aims to make superfast and ultrafast broadband available to as many homes and businesses across Essex as possible. GBF funding extended the Superfast Essex Phase 4b rollout programme to reach additional rural areas. | Success Essex | 477256 | Yes, GBF funding will be spent in full by 31 March 2023 | To mitigate delays caused by the extended time period taken by BDUK to approve the addition of the GBF funding to the project, surveys required to assess the quality of the existing broadband infrastructure and to validate the costings at all identified sites have been carried out. This has ensured that the project is fully planned, however, these surveys have identified that the costs associated with a number of the properties will be higher than forecast. The cost increases have arisen as a result of: increases in infrastructure costs (including a 70% increase in fibre cable pricing), increased cost of traffic management (due to reduced availability of workforce and due to the need to redesign works to avoid priority routes to vaccination centres) and reduction in workforce due to Brexit. | If additional GBF funding is not awarded, 79 out of the 300 rural business premises identified will not be able to benefit from the growing digital economy and may lose momentum in the COVID-19 economy. Additionally, 185 of the 1,200 rural residences identified will be left without even a basic superfast broadband service. The supplier and Essex County Council have worked collaboratively to maximise the reach of the GBF investment and estimate that a further 110 premises would benefit from the work detailed in the application. Without the additional funding, these properties will not benefit. | N/A | Strong | Programme appears to be based on the understanding that the GBF funding will be awarded in September 2022. Need to confirm the programme with Paul as funding will not be awarded until November 2022. Can project still be delivered by March 2023? Need to confirm whether it will be possible for the GBF funding to be claimed by March 2023. Currently appears to be a delay in drawing down the funding from ECC.
Jaywick Market and Commercial Space - the project includes the build of a covered market and affordable business space on a gateway site in Jaywick Sands to support the local economy, grow local entrepreneurship, and grow and retain economic activity and job creation in the local area, which is the most deprived in the country. | Success Essex | 419060 | Yes, GBF funding will be spent in full by 31 March 2023 | Additional GBF funding is required to help mitigate the costs associated with the discovery of asbestos and other ground obstructions during excavation. Additional costs incurred to date total £219,060 but it is estimated that these costs could rise to £450,000. In addition, due to the increase in construction costs due to the COVID-19 pandemic, Brexit and high inflation levels, elements of the original project scope have been removed to try and keep costs within budget. Elements removed include solar panels, bin storage, cafe fit out, CCTV, internal signage and the IT required to provide a hybrid learning space. | If additional GBF funding is not awarded, work to deliver the car park (where excavation work is ongoing) will need to be paused. The car park will need to be redesigned and planning permission for the revised design sought further delaying the project. In addition, there may be insufficient funding resulting in the project not being completed leading to missed opportunities to improve skills levels in the area and to reduce unemployment through the provision of low cost starter units for new and emerging businesses. If the omitted items cannot be returned to the project scope, this will be less devastating but will mean that the following items are not delivered: roof solar panels, storage for bins, fit out of the cafe, CCTV over the community garden area, information technology requirements both in the commercial units and in the meeting room and internal signage. | N/A | Strong | Elements of the requested additional funding are speculative but can be used to deliver elements of the scope which have been removed if the costs associated with excavating the car park and area surrounding the building are lower than expected.
Enterprise Centre for Horizon 120 Business and Innovation Park - delivery of a new 3,100 sqm Enterprise Centre building with a variety of office spaces. There will also be a flexible conference space that can be transformed into smaller units. It is a purpose built physical and virtual environment designed to drive collaboration, encourage idea generation and underpin problem solving. | Success Essex | 907124 | Yes, GBF funding will be spent in full by 31 March 2023 | Additional GBF funding is required for the following reasons: • Additional costs for construction, security and supply chain issues as a result of the COVID-19 pandemic, including increased security costs incurred for a 35 week period as a result of a delayed start to construction due to construction and supply chain delays, additional costs associated with a 10 week delay during construction due to supply chain issues and costs associated with the removal of a spoil mound of 5,000 cubic metres. • Enabling works for the extension of the existing car park - to better enable the optimisation of the existing facilities, it is necessary to further increase the availability of car parking at the site. | The project will be delivered in accordance with the Business Case as cost increases have been absorbed by Braintree District Council. However, this additional Council investment will impact negatively on their ability to undertake further development on the wider business park impacting on the total number of additional jobs created and will reduce the level of funding available to support other employment related projects. | N/A | Medium | Full scope of Business Case will be delivered through additional Braintree DC funding. This leads to implications for other projects but not for this project specifically.
Tendring Bikes and Cycle Infrastructure - the project will deliver a bespoke bike scheme and cycle network infrastructure within Jaywick Sands and Clacton aimed at tackling inequality within one of the most deprived areas of the country. | Success Essex | 300200 | Yes, GBF funding will be spent in full by 31 March 2023 | It was originally intended that 1,620 bikes would be provided for use in the bike loan scheme, however, due to increased supply chain costs it has only been possible to procure 1,300 bikes. Additional GBF funding would allow purchase of an additional 422 bikes, including 10 adapted bikes and 50 electric bikes. There are over 200 eligible applications for a bike but due to current funding constraints, not all applicants will be successful. Provision of electric bikes would expand the reach for labour market and job opportunities. | The project will still be delivered in accordance with the Business Case if the additional funding is not awarded. The additional funding would allow the opportunity to offer adapted bikes and e-bikes to people as appropriate and increases the capacity to support people who were previously economically inactive to consider new jobs, skills and opportunities. | N/A | Weak | Additional funding would not only allow project to be delivered as per the Business Case but goes beyond that to include items not originally specified in the Business Case. Weak case for additional funding as benefits expected from Business Case can be achieved without additional funding
Restoring the Glory of the Winter Garden - Phase 2 - Establishment of a new facility, Racquet Studios, in the Winter Garden. Racquet Studios would be a world class facility for virtual film production, a centre of excellence for skills training in digital and creative arts and a leading virtual film production research and development facility. | TES | 900000 | Yes, GBF funding will be spent in full by 31 March 2023 | N/A | N/A | The Business Case suggests that if the GBF funding is not awarded, the works will not be forthcoming at this time. Work has been undertaken which has concluded that the only option for bringing this work forward is through public sector funding. Eastbourne Borough Council has committed significant funding to the wider Devonshire Quarter project but their ability to deliver the full scope of the project has been impacted by cost increases. | Strong | Need to confirm the programme with Alex. Contractor procurement undertaken in advance of funding award allowing works to start onsite in November? Key dates suggest planning and listed building consent, procurement and construction commencement will all be achieved in November 2022
Seven Sisters Country Park Visitor Infrastructure Uplift - the project delivers a comprehensive refresh of the visitor offer at the Country Park, including 233 sqm of new retail space for local businesses and accommodation for the Site Warden. | TES | 84100 | Yes, GBF funding will be spent in full by 31 March 2023 | The costs included within the original application for GBF funding were based on tenders received in 2020/21. These works needed to be reprocured and this resulted in significantly increased construction costs. These increases were due to supply and demand issues resulting in extended lead in times and increased costs, increasing labour costs, inflation and rising transportation costs. Additional internal funding has been secured to cover other construction cost increases but funding is not currently available to cover the increase in construction contract price. | If additional funding is not awarded, there will be a need to value engineer elements of the project, resulting in reduced outputs and outcomes. It may not be possible to fit out the cottages and the pump barn fully leading to a reduction in tourism opportunities and a negative impact on the spend per head outlined in the Business Case. In addition, fewer units will be ready and available for use by local businesses, meaning a reduction in the number of enterprises supported by the project. | N/A | Strong
Observer Building, Hastings - the project will support the full redevelopment of the 4,000 sqm Observer Building, which has been empty and increasingly derelict for 35 years, into a highly productive mixed-use building, creating new homes, jobs, enterprise space and support. | TES | 315000 | Yes, GBF funding will be spent in full by 31 March 2023 | Additional GBF funding is required due to significant cost increases encountered during the procurement process. The cost increases have arisen as a result of supply chain issues arising from both the COVID-19 pandemic and Brexit, rising inflation levels and longer lead in times for some items. Value engineering and additional fundraising have been undertaken and it has been possible to complete most of the works included in the contract. However, it has not been possible to fully fund the replacement of the windows and the repairs to the facade of the building. | If additional funding is not awarded, the facade works cannot be completed. This will either result in scaffolding being left up (at a cost of £800 per week) or the scaffolding being removed only to be replaced at a later date to allow the work to be completed. In addition, without additional funding there is not currently sufficient funding available to install the replacement windows on one side of the building. If additional funding is not awarded, these works will need to be funded through loan finance which will mean that other non-essential works including the facade works will not be completed at this time. | N/A | Medium | Medium strength - it sounds as if there is sufficient funding to deliver the essential works. GBF funding would release loan funding to carry out other less essential works at a later date.
Accessing Charleston: Removing the Barrier to Growth (project extension) - establishing a low carbon way for visitors to access Charleston through provision of electric vehicle charging points in the car park and purchase of a electric minibus to convey people to the site from rail and bus stations. | TES | 321414 | Yes, GBF funding will be spent in full by 31 March 2023 | N/A | N/A | The Business Case suggests that if the GBF funding is not awarded, the works will not be forthcoming. This will mean that as a result of increasing visitor numbers, there will be a increase in carbon emissions and congestion on local roads as visitors all travel by car. If the proposed works are not delivered, this will limit Charleston's ability to grow the number of visits from people travelling from outside the immediate area (assuming they are not travelling by car) and will limit Charleston's ability to diversify their audience by excluding people who do not have access to a car including younger people and those from lower socio economic backgrounds. | Weak | Weak case for investment as benefits are likely to be limited and very Charleston focused. Limited benefit for the wider area. Alternative options are available but would not be palatable in terms of passing the cost onto visitors.
Sussex Innovation, Falmer - COVID secure adaptions (Hybrid Working Enhancements) - further development on the site to enable more effective hybrid working, including investment in technology (laptops and server upgrade), building enhancements, enhanced hygiene facilities and sustainable transport investment. | TES | 200000 | Yes, GBF funding will be spent in full by 31 March 2023 | N/A | N/A | If the works to enable more hybrid working are not taken forward, this is likely to lead to a lower occupancy level of business tenants in the centre. This will in the short-term lead to a reduction in income and a reduction in the number of staff employed directly by the centre. In the long term it may be unsustainable to run the centre with such a low occupancy level and therefore it is possible that the centre may have to shut down if the running costs are not matched by the income from commercial rents. The Business Case suggests that there is no other funding available to deliver these works and therefore it is assumed that if GBF funding is not awarded, that the works will not come forward. | Weak | GBF funding has only recently been spent delivering improvements to the Centre. It is unclear whether the latest proposed improvements strengthen the benefits realised by those works or seek to change the direction of the centre. Concern over whether benefits achieved through original GBF investment be short-lived.

## Project benefits and VfM
Getting Building Fund - applications for additional funding
Project benefits and VfM
Project name and brief description (max 50 words) Formula - please do not edit cell | Federated Area Formula - please do not edit cell | Benefit Cost Ratio (as set out in project Business Case) (to be completed for all applications for funding) | What is the expected impact on the Benefit Cost Ratio of the additional GBF funding sought? (for projects seeking funding to deliver existing Business Cases only) | Key project benefits (to be completed for all projects seeking GBF funding through this process. For those projects seeking funding to deliver an extension, this should only set out those benefits associated with the additional funding) | Have the project benefits changed since the Business Case was submitted? If so, what has changed and what is the likely impact on the value for money offered by the project? (for projects seeking funding to deliver existing Business Cases only) | Additionality that will be achieved through the award of additional GBF funding. (include reference to any elements of the original project scope which it will not be possible to deliver without additional GBF funding or any additional work that needs to be completed to facilitate realisation of the forecast project benefits outlined in the Business Case.) | Change in project benefits since original Business Case submission (assume award of additional GBF funding) | Estimated value for money of project (assume award of additional GBF funding) | Comments
Thanet Parkway Railway Station - A new railway station on the Ashford International – Ramsgate railway line at Cliffsend with associated level crossing/signalling upgrades to improve accessibility to rail in Thanet, which is a historically economically disadvantaged part of the county. | KMEP | Very High (Conventional BCR was not reported as the project will generate revenues that are greater than the costs which would result in a net 'negative' cost, and therefore a 'negative' BCR. Net Present Value used as a measure of return from investment) | Calculations have been undertaken which demonstrate that, subject to the total project cost remaining below £54.2m, the project will continue to offer High value for money. Total project cost is currently reported to be £43.9m. | • Accelerate the pace of housing delivery in Thanet - 1,600 to 3,200 additional homes delivered within 30 years of station opening • Positively contribute to economic growth by attracting higher skilled workers to the area • Stimulate the creation of additional jobs by encouraging business location and expansion decisions based on the existence of the new station - creation of 400 to 800 additional jobs within 30 years of station opening | The forecast project benefits have not changed. However, the increased scope of the archaeological findings will bring further benefits to the area through the increased knowledge and understanding of this potentially nationally significant site and its contribution to the historical records for Thanet. | No direct additionality as a result of additional GBF funding as the full scope of works would need to be completed, regardless of award of additional GBF funding, to allow the station to safely open. However, additional GBF funding will ensure full delivery of the project scope by safeguarding delivery of the level crossing works, which are essential for the station to open thus securing the forecast benefits. The funding will also help safeguard the full completion of the archaeological excavations that will bring further benefits to the area, as well as increased employment and safeguarding of jobs from Thanet Parkway beyond what was originally forecast. | Project benefits unchanged | Expected to remain comfortably above 2:1 | No real additionality offered as a result of additional GBF funding. KCC have made efforts to secure funding from alternative sources i.e. New Stations Fund 3.
Innovation Park Medway - Sustainable City of Business - delivery of one section of 'The Runway Park' on the northern site of Innovation Park Medway. The Runway Park will be a primary forum for collaboration, bringing businesses and individuals together to foster an innovative spirit, and enable businesses to interact with the wider community. | KMEP | 5.3:1 | It is expected that if additional GBF funding is awarded, the BCR will reduce to 3.8:1 | Key project benefits include: • Creation of 310 new gross highly skilled jobs in engineering and technology by 2023/24. These jobs will facilitate the upskilling of the local workforce • Creation of 6 new construction jobs • Enabling 6,800 sqm of commercial workspace (B1 and B2) | The benefits remain unchanged since the Business Case was submitted. | The additional GBF investment will enable all elements of the original project scope to be delivered to the high quality envisaged for the site as set out in the IPM Design Code. Without the additional investment, the materials used for certain elements of the project are likely to need to be value engineered which would require a further review from planning and would lead to a further delay in project delivery. | Project benefits unchanged | Expected to remain comfortably above 2:1
Javelin Way Development - Delivery of light industrial units which act as an enabling development in order to deliver the Jasmin Vardimon Dance Laboratory in Ashford. | KMEP | 2.45:1 | BCR is expected to reduce to 2.37:1 | The key project benefits are: • construction of a 'Creative Laboratory' production space (with a ground floor internal area of 1,293sqm) • development of light industrial units (with a gross internal floor area of 3,046sqm) • accommodate up to approximately 176 full-time equivalent employees, in addition to 21 freelance and contractor opportunities • deliver opportunities for business development in the creative sector | At the outset of the project it was indicated that 29 industrial units would be delivered, subject to market demand. A number of occupiers are seeking to take more than 1 unit and combine them into a single unit. This has resulted in a smaller number of units being delivered but the floor space provided remains unchanged. | Due to increased costs there has been a requirement for the quality of the fit out to be reduced and for some elements of the project, including delivery of solar panels, to be removed from the project scope. Additional funding will allow these elements to be re-examined. | Project benefits unchanged | Expected to remain comfortably above 2:1 | BCR calculated in the Business Case but project now appears to be relying on Value for Money exemption 1. No firm commitment that elements removed from the project scope will be returned if additional funding is awarded. The funding may just be used to replace the additional funding already committed by KCC.
Techfort Phase 2, The Citadel, Dover - refurbishment of Casemates 53 and 54 to accommodate a unique mix of cultural uses, small businesses and craft workshops. | KMEP | 5.85:1 | N/A | Key project benefits include: • employment outcomes - 19 employees and 4 trainees • a total of 8,152 sq ft of space available for a mix of creative businesses • urgent restoration works to bring the heritage asset back in use by the end of March 2023 • public access to 5 acres of the site • further improvement to public realm available for an anticipated minimum of 3,000 visitors to the site • additional educational opportunities for learners and art/craft participation • increased footfall and potential for additional events | N/A | It is understood that the proposed works will not be undertaken in the short-term if GBF funding is not awarded. This will mean that Casemates 53 and 54 will not be returned to effective use and the associated benefits will not be realised without GBF investment. | N/A - new Business Case | Expected to remain comfortably above 2:1
Discovery Park Incubator - Delivery of new incubator, self contained laboratory units, informal break out area and shared lab support facilities in Building 500 at Discovery Park | KMEP | 4.74:1 | It is expected that the BCR will reduce to 4.49:1 if additional GBF funding is awarded. | Key project benefits include: • Additional businesses located at Discovery Park • Existing businesses retained at Discovery Park (through access to facilities or relationships with other firms) • Increased business-to-business and business-to-knowledge base collaboration • Increased business survival and increased growth through access to innovation support and facilities • Additional commercial investment in Building 500 • Additional employment in firms located at the Incubator • Additional businesses locating elsewhere at Discovery Park | The project benefits remain unchanged since the Business Case was submitted. | If additional GBF funding is awarded, it will allow refurbishment of break-out areas and shared laboratory equipment. These works are currently at risk due to the increased project costs. In addition, a former redundant specialist Containment Level 3 laboratory facility for hazardous microbiological research activities will be recommissioned and brought online for potential occupiers. This is a highly specialised facility and the costs of refurbishment and complexity of engineering are prohibitive for prospective occupiers. | Project benefits unchanged | Expected to remain comfortably above 2:1
Extension of the existing Phase 2 ASELA LFFN project - GBF funding has been requested to extend the LFFN project into Phase 3 allowing more areas in South Essex to benefit from the roll-out of full fibre infrastructure. | OSE | Value for Money exemption applied | N/A | The scale of the additional benefit offered by the GBF funding is unclear as there are references to the benefits provided in the original GBF Business Case but it is expected that the additional GBF funding will allow fibre infrastructure to be extended into areas within the South Essex region which have not yet benefited from investment. A number of more general benefits associated with the provision of fibre infrastructure are set out in the Business Case. | N/A | It is understood that the proposed works will not be undertaken in the short-term if GBF funding is not awarded. The scale of benefits that will be realised as a result of the investment is unclear but it is expected that the investment will allow fibre infrastructure to be extended into areas which have not previously benefited from investment. | N/A - new Business Case | Unknown - Value for Money exemption applied | ITE report needed to provide greater clarity on the economic case and VfM offered by the project. Business Case is unclear on the additional benefits that will be realised as a result of the additional investment and refers to the previous Business Case.
Tindal Square, Chelmsford - creation of a new civic public square of over 3,000 sqm that provides a destination space for arts, events and celebrations outside Shire Hall in Chelmsford City Centre. | Success Essex | Value for Money exemption 1 applied | Not discussed in application as BCR not calculated | The key project outcomes as detailed in the Business Case are: • Creation of 50 construction jobs • Creation of 100 jobs associated with the renewed use of the Shire Hall • Increased footfall and dwell time in the city centre • Estimated £10m economic impact based on £1 per £3 investment • Improved air quality and modal shift due to removal of motorised traffic and introduction of new cycle connections | The project benefits remain unchanged | The additional funding will ensure that the full project scope, as per the approved Business Case, can be delivered. This will safeguard the forecast project benefits and deliver maximum benefit to the City Centre. Without the additional funding, it will not be possible to deliver the full scope as per the Business Case due to increased project costs. | Project benefits unchanged | Unknown - Value for Money exemption applied | Value for Money exemption 1 applied in original Business Case. No commentary provided in application to provide assurance that the project continues to offer High value for money. Any additional information available as to which elements of the project would not be forthcoming if additional funding is not awarded and likely impact on benefits?
Extension of the full-fibre broadband rollout in Essex to reach rural and hard to reach premises - Superfast Essex is a broadband improvement programme run by Essex County Council. The programme aims to make superfast and ultrafast broadband available to as many homes and businesses across Essex as possible. GBF funding extended the Superfast Essex Phase 4b rollout programme to reach additional rural areas. | Success Essex | 31.2:1 | It is expected that the BCR will reduce to 25.7:1 if the additional GBF funding is awarded. | The deployment of superfast broadband infrastructure for use by the public and businesses is expected to result in the creation of 300 new jobs, 300 businesses assisted with gigabit connections and 1,200 residences provided with gigabit broadband. In addition, the project will reduce economic disadvantage through improving internet connectivity and will underpin the future rollout of improved mobile communications technology as the fibre network being installed will be available for use by 5G networks. | The project benefits remain unchanged from the Business Case but there is the potential for additional benefits to be realised if additional GBF funding is awarded. | The additional GBF funding will allow gigabit broadband to be connected to 79 rural business premises and allow them to benefit from the growing digital economy and better compete in an economic environment that is more focused on online trading and digital customer engagement. Additionally, 185 rural residences will benefit from a new gigabit capable broadband service. This gigabit connection will future proof broadband residents against increased connectivity requirements in the future. This planned infrastructure will ultimately allow residents to compete in the global market for remote workers. | Project benefits unchanged | Expected to remain comfortably above 2:1 | Question on additionality needs to be answered if the project is to prioritised for funding. Presumably this would be the properties which would otherwise be removed from the project scope?
Jaywick Market and Commercial Space - the project includes the build of a covered market and affordable business space on a gateway site in Jaywick Sands to support the local economy, grow local entrepreneurship, and grow and retain economic activity and job creation in the local area, which is the most deprived in the country. | Success Essex | Original BCR was 5:1. This reduced to 3.77:1 following procurement | It is expected that the BCR will reduce to 3.45:1 if the requested additional GBF funding is awarded | The key project benefits are: • net additionality of 39 FTE jobs by year 4 • 842sqm net lettable commercial floorspace • 12% increase in employment density • Increased attractiveness of Jaywick Sands to developers and businesses • Improved access to affordable healthy food and household goods for residents • Decreased deprivation | Since submission of the original Business Case, the project has adapted and additional benefits are now forecast. These benefits have been achieved through redesign of the managed workspace units resulting in delivery of 11 multi-use units which will be flexible and able to provide accommodation for more businesses. This change has resulted in the number of new jobs rising to 45. | The receipt of additional funding will allow delivery of the project to complete, including delivery of the car park although it is likely that there will still be elements of the original scope which will not be delivered. Without the additional funding, the additional costs associated with the excavation will not be met and this will result in work on the car park being stopped. | Project benefits increased | Expected to remain comfortably above 2:1 | Updated BCR calculation provided.
Enterprise Centre for Horizon 120 Business and Innovation Park - delivery of a new 3,100 sqm Enterprise Centre building with a variety of office spaces. There will also be a flexible conference space that can be transformed into smaller units. It is a purpose built physical and virtual environment designed to drive collaboration, encourage idea generation and underpin problem solving. | Success Essex | 3.054:1/9.331:1 | The BCR will marginally increase as a result of additional GBF funding as additional benefits will be realised. | The key project benefits are: • Jobs created - 496 (over 4 years) • Additional Construction jobs – 70 FTE • Jobs safeguarded – 150 • 2,845sqm of commercial floorspace delivered • 200 business/institutions assisted | The project benefits remain unchanged, however, additional GBF funding will allow realisation of additional benefits. | If the additional GBF funding is awarded, the following additional benefits will be realised: • Additional jobs created - 32 (over 4 years) • Additional construction jobs - 87 FTE (includes adjustment from original Business Case) | Project benefits unchanged | Expected to remain comfortably above 2:1 | Application form indicates that BCR would increase if additional funding is awarded. Application indicates additionality in the form of additional benefits but also indicates that benefits remain unchanged from the Business Case. Funding request potentially should have been through a new Business Case and not an application form. BCR used when project originally awarded funding was 3.054:1 but BCR quoted on application form was 9.331:1 which was also referenced in the Business Case.
Tendring Bikes and Cycle Infrastructure - the project will deliver a bespoke bike scheme and cycle network infrastructure within Jaywick Sands and Clacton aimed at tackling inequality within one of the most deprived areas of the country. | Success Essex | 2.12:1 | It is expected that there will be a marginal impact on the BCR. The additional bikes will enable additional benefits to be realised, partially offsetting the cost increase. Analysis has been undertaken which demonstrates that the BCR should remain above 2:1 | The key project benefits are: • Increase cycling participation to level up inequalities • Increase sustainable active travel through cycling, including developing local cycling infrastructure • Increase the employability of local people and improve the local economy, including access to employment, education, and training opportunities. • Increase the fitness and physical health of inactive people • Increase the mental wellbeing of inactive people and support to be job ready • Increase the resilience, connectedness and social capital in local communities | The benefits remain unchanged. However, award of additional GBF funding would allow additional benefits to be realised. | The award of additional GBF funding would allow the purchase of additional bikes for use in the cycle loan scheme. This would allow the scheme to reach more people, including those requiring adapted or e-bikes, and would increase the number of people who had greater access to jobs and other opportunities, including training. | Project benefits increased | Expected to be around 2:1
Restoring the Glory of the Winter Garden - Phase 2 - Establishment of a new facility, Racquet Studios, in the Winter Garden. Racquet Studios would be a world class facility for virtual film production, a centre of excellence for skills training in digital and creative arts and a leading virtual film production research and development facility. | TES | Value for Money exemption 1 applied | N/A | Key project benefits include: • creation of a minimum of 10 new direct and indirect jobs • increased inward investment in local service and creative industry economy • Training programmes will stimulate more opportunities for the local population to become involved in a highly skilled creative industry • The digital media/virtual film production facility will deliver opportunities for existing/traditional filmmaking businesses and partnerships. | N/A | These works will not be completed without award of GBF funding and therefore the additionality is: • Delivery of Racquet Studios including provision of LED volume screens and other equipment including production lighting, AV and IT • Fit out and structural works | N/A - new Business Case | Value for Money exemption applied | Steer have raised queries regarding which benefits and costs have been included in the BCR. Therefore there is a risk that the BCR could change bringing the BCR down to below 2:1
Seven Sisters Country Park Visitor Infrastructure Uplift - the project delivers a comprehensive refresh of the visitor offer at the Country Park, including 233 sqm of new retail space for local businesses and accommodation for the Site Warden. | TES | Value for Money exemption 1 applied | Not discussed in application as BCR not calculated | The benefits which are dependent upon the GBF funding include: • Creation and safeguarding of a total of 6.5 FTE jobs • Creation of 1 x 1 bed flat for the onsite warden • 131 sqm of high footfall retail space • 1 new superfast Broadband connection • 100 enterprises supported through the new retail space • Increased visitor spend • Increased footfall | The project benefits have not changed since the Business Case was submitted. However, the benefits will not be fully realised if additional GBF funding is not awarded. | Additional GBF funding will safeguard realisation of the benefits outlined in the Business Case. If additional funding is not awarded, the following benefits will likely be lost: • 79 enterprises will be supported, rather than the intended 104. The reduction in enterprises is likely to also impact on wider project sales due to the loss of certain key products • Spend per head likely to reduce from £3.90 per visitor to £2.93 • Reduced visitor numbers at the visitor centre and Pump Barn, particularly during the low season (October to March) which will have an impact on the sustainability of existing employment and the ability to create new jobs. | Project benefits unchanged | Unknown - Value for Money exemption applied
Observer Building, Hastings - the project will support the full redevelopment of the 4,000 sqm Observer Building, which has been empty and increasingly derelict for 35 years, into a highly productive mixed-use building, creating new homes, jobs, enterprise space and support. | TES | 2.17:1 (taken from the most recent Business Case seeking GPF funding) | The BCR will reduce if additional GBF funding is awarded. If an additional £315,000 is awarded, the BCR will reduce to 2.14:1. | The key project benefits are: • 2,100 sqm of new commercial space • 81,000 kg of CO2 emissions avoided • 120 gross operational FTE jobs, including 40 re/entrants to the labour market • 40 enterprises receiving non-financial support | The benefits have changed since the submission of the GBF Business Case, however, they remain in line with those included in the most recent Business Case update when the project was seeking GPF funding. Benefits have increased since the submission of the approved GBF Business Case. | The award of additional GBF funding would allow the order of the tiles required for the façade works and would fund the installation of the new windows. This will release loan funding to allow the completion of the façade improvements. Without the additional funding, it will not be possible for the façade works to be completed at this time. Completion of the façade works will help identify the Observer Building as a new destination building in the centre of Hastings. | Project benefits unchanged | Expected to remain comfortably above 2:1 | 2 options included in the application - £315,000 and £650,000 additional GBF funding. £650,000 additional funding would reduce the BCR to 1.97:1 and has therefore not been included as an option.
Accessing Charleston: Removing the Barrier to Growth (project extension) - establishing a low carbon way for visitors to access Charleston through provision of electric vehicle charging points in the car park and purchase of a electric minibus to convey people to the site from rail and bus stations. | TES | Value for Money exemption 1 applied | N/A | The key project benefits are: • Creation of 2 year round front facing jobs at Charleston and increased tourism spend in the local economy • Provision of increased sustainable transport to Charleston and the South Downs National Park resulting in a reduction of CO2 emissions projected at between 222,000 and 444,000 kg per annum • Growth in new visitors arriving by other means than car journeys from 5% to 20% within 3 years. | N/A | These works will not be completed without award of GBF funding and therefore additionality will be: • Purchase of a 16 seater electric minibus to provide a scheduled timetable from Lewes railway station to Charleston • Provision of 3 electric vehicle charging points at Charleston, which would also be available for visitors to the South Downs National Park | N/A - new Business Case | Unknown - Value for Money exemption applied | There is very limited detail in the Economic Case and therefore it cannot be determined whether the project meets the criteria for the Value for Money exemption.
Sussex Innovation, Falmer - COVID secure adaptions (Hybrid Working Enhancements) - further development on the site to enable more effective hybrid working, including investment in technology (laptops and server upgrade), building enhancements, enhanced hygiene facilities and sustainable transport investment. | TES | Value for Money exemption 1 applied | N/A | The key project benefits would be: • Reduction in carbon emissions • Cleaner, greener environment • Better environment for local businesses, fuelling economic growth • 180 jobs safeguarded • 90 new jobs created | N/A | These works will not be completed without award of GBF funding and therefore additionality will be: • Investment in technology - provision of additional laptops and workstations, server room upgrade and contactless door entry system • Building enhancements - alterations to the building to provide Zoom rooms (sound proof booths for video calls), break out facilities, outdoor meeting facilities and social space • Investment in enhanced hygiene facilities - air conditioners which draw in outside area • Sustainable Transport Investment - provision of electric vehicle charging points and secure cycle parking. | N/A - new Business Case | Unknown - Value for Money exemption applied | There is very limited detail in the Economic Case and therefore it cannot be determined whether the project meets the criteria for the Value for Money exemption. Very little information provided on expected benefits. Significant gaps remain within the Business Case

## Risks to project delivery
Getting Building Fund - applications for additional funding
Risks to project delivery
Project name and brief description (max 50 words) Formula - please do not edit cell | Federated Area Formula - please do not edit cell | Expected project completion date | Can the existing project proceed without additional GBF funding? For projects which are seeking additional funding to deliver the original Business Case | What are the main risks impacting the ability of the project to proceed? This information should be provided for all applications, including those for extensions to existing projects | If GBF is awarded, are there any remaining barriers to project delivery? | What are the remaining barriers to project delivery? | Comments
Thanet Parkway Railway Station - A new railway station on the Ashford International – Ramsgate railway line at Cliffsend with associated level crossing/signalling upgrades to improve accessibility to rail in Thanet, which is a historically economically disadvantaged part of the county. | KMEP | New station is expected to open on 22 May 2023 | Yes, but potentially with an adverse impact on project completion date | The main risks relate to the level crossing and signalling work which must be completed to allow the station to safely open to the public, including: • Funding risks due to inflationary pressures across the construction industry and early stage of design • Procurement of equipment due to significantly extended lead in times, although the equipment has now been secured. • Risks to delivery timescales given conflicting track works due to take place in the same period. | Yes - there are remaining barriers to project delivery which may impact on completion date | Resolution needs to be reached with regard to the conflicting track works to ensure that the station can open in May 2023 as planned. If these conflicts cannot be resolved, the opening of the station may be delayed. | There remains a risk around the cost of the level crossing works. Detailed design for these works has not yet been undertaken and therefore there remains a risk of further cost increases.
Innovation Park Medway - Sustainable City of Business - delivery of one section of 'The Runway Park' on the northern site of Innovation Park Medway. The Runway Park will be a primary forum for collaboration, bringing businesses and individuals together to foster an innovative spirit, and enable businesses to interact with the wider community. | KMEP | March 2023 | Yes, but with an adverse impact on the project outputs and outcomes | The main risks impacting the ability of the project to proceed are: • Additional GBF funding is not forthcoming - this will result in the quality of the IPM site being reduced and value engineering being employed • Planning consent is not forthcoming - there is a risk that alternative materials will not meet the requirements of the design code and LDO for the site • No/fewer private sector businesses are interested in building on the site - this will delay realisation of the forecast employment benefits. | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery
Javelin Way Development - Delivery of light industrial units which act as an enabling development in order to deliver the Jasmin Vardimon Dance Laboratory in Ashford. | KMEP | December 2022 | Yes, but with an adverse impact on the project outputs and outcomes | Delivery of the project has been significantly impacted by utility delays. There remain a few utility connection issues but these should be complete by the end of 2022. There is one industrial unit which is not yet under offer. All other units are under offer but there remains a chance that some of these agreements could yet fall through. | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery | Are the remaining utility works a barrier to delivery? Could they impact on the project completion date?
Techfort Phase 2, The Citadel, Dover - refurbishment of Casemates 53 and 54 to accommodate a unique mix of cultural uses, small businesses and craft workshops. | KMEP | Believed to be March 2023 | N/A - new Business Case | The main risks impacting the ability of the project to proceed are: • GBF funding is not awarded • There is a lack of demand for the Casemates • There is weaker than expected public interest in the development • Capital costs exceed the available budget • Release of conditions attached to the planning and scheduled monument consents. | Yes - there are remaining barriers to project delivery which may impact on completion date | Whilst planning and Scheduled Monument consent have been secured there is a requirement for Historic England to release conditions on the Scheduled Monument consent | May potentially be a bit harsh to say there are barriers to delivery due to planning and scheduled monument conditions as this has not been referenced for any other projects. But for other projects which are further progressed all conditions may have already been discharged.
Discovery Park Incubator - Delivery of new incubator, self contained laboratory units, informal break out area and shared lab support facilities in Building 500 at Discovery Park | KMEP | December 2022 | Yes, but with an adverse impact on the project outputs and outcomes | The only identified risk relates to the current need for additional funding to ensure that the full scope of the project can be delivered. SELEP potential concern around lead-in time for any specialist equipment needed to complete the work in the Level 3 laboratory facility. | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery | Consideration does not seem to have been given to the risk of extended lead in times for specialist equipment. KMEP concerns regarding delivery of project by March 2023 as progress to date has been slow.
Extension of the existing Phase 2 ASELA LFFN project - GBF funding has been requested to extend the LFFN project into Phase 3 allowing more areas in South Essex to benefit from the roll-out of full fibre infrastructure. | OSE | March 2023 | N/A - new Business Case | No risk register is provided in the Business Case but it is indicated that any risks to project delivery will be minimised as project governance is already in place with the current contractors and any risks are being addressed as they are identified. | No - there are no remaining barriers to project delivery | The project will be a continuation of the existing GBF project which is nearing completion and therefore all required processes are in place.
Tindal Square, Chelmsford - creation of a new civic public square of over 3,000 sqm that provides a destination space for arts, events and celebrations outside Shire Hall in Chelmsford City Centre. | Success Essex | January 2023 | Yes, but with an adverse impact on the project outputs and outcomes | The risks impacting the ability of the project to proceed are: • the potential need to reduce the project scope due to increased costs • requirement for utilities companies to complete necessary diversions. Programme for these works impacted by availability of labour • extended lead in times for remaining key materials and supplies | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery | In the assessment undertaken by Paul, no barriers to delivery are indicated but this assessment reflects contents of the application form. I think the risk is more to the programme, rather than the utilities diversions never happening.
Extension of the full-fibre broadband rollout in Essex to reach rural and hard to reach premises - Superfast Essex is a broadband improvement programme run by Essex County Council. The programme aims to make superfast and ultrafast broadband available to as many homes and businesses across Essex as possible. GBF funding extended the Superfast Essex Phase 4b rollout programme to reach additional rural areas. | Success Essex | January 2023 | Yes, but with an adverse impact on the project outputs and outcomes | The primary risks impacting the ability of the project to proceed are: • Funding deadlines - delivery profiles are confirmed for January 2023 delivery, ahead of the March 2023 deadline • Highway permits - highway permits are secured to allow the project to complete in January 2023 • Multi-dwelling unit delivery - internal build to flats is reliant on landowner and resident permission. The supplier has a dedicated team who are working on progressing these permissions. The only unmitigated risk is the need for additional funding to bridge the identified funding gap. | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery
Jaywick Market and Commercial Space - the project includes the build of a covered market and affordable business space on a gateway site in Jaywick Sands to support the local economy, grow local entrepreneurship, and grow and retain economic activity and job creation in the local area, which is the most deprived in the country. | Success Essex | March 2023 | Yes, but with an adverse impact on the project outputs and outcomes | The main risks impacting the ability of the project to proceed are: • Additional funding not received - this will mean that work on the car park will need to be paused. • Overspend on the current budget - this will mean that the building will not be opened which will have implications for the local area • Reduced demand for commercial space and market pitches - this may mean that some units and market pitches remain vacant • Unexpected or worse than expected ground conditions or contamination - this risk has been realised for the main building site but remains a risk for the car park • Running costs higher than anticipated | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery | The excavation of the car park and areas surrounding the building has not yet commenced. Therefore risks remain around the discovery of further asbestos and ground obstructions.
Enterprise Centre for Horizon 120 Business and Innovation Park - delivery of a new 3,100 sqm Enterprise Centre building with a variety of office spaces. There will also be a flexible conference space that can be transformed into smaller units. It is a purpose built physical and virtual environment designed to drive collaboration, encourage idea generation and underpin problem solving. | Success Essex | September 2022 | Original GBF project can be delivered without additional funding but extra funding would allow realisation of additional outputs/outcomes | No risks to project delivery have been identified. It is understood that the building is now complete and has been formally opened. However, the status of the car park extension works is unclear. | No - there are no remaining barriers to project delivery | No remaining barriers to project delivery | No information given on risks to project delivery. Main works complete but unclear if there are risks associated with the car park extension works, i.e. extended lead in times for materials etc. Unclear if project completion date includes car park extension works and removal of spoil mound
Tendring Bikes and Cycle Infrastructure - the project will deliver a bespoke bike scheme and cycle network infrastructure within Jaywick Sands and Clacton aimed at tackling inequality within one of the most deprived areas of the country. | Success Essex | January 2023 | Original GBF project can be delivered without additional funding but extra funding would allow realisation of additional outputs/outcomes | The main risks impacting the ability of the project to proceed are: • Lead in times for the new bikes - this has been mitigated through pre-ordering a bulk order of bikes • Increasing cost of standard bikes - this has been mitigated through negotiation of a fixed price with the supplier • Increasing cost of e-bikes or adapted bikes - this will be mitigated by either reducing the number of bikes ordered or by purchasing more standard bikes at the agreed fixed price. | No - there are no remaining barriers to project delivery | There are no remaining barriers to project delivery | Lead in times for bikes is reduced due to there being a pre-arranged bulk order from which the required bikes can be purchased immediately.
Restoring the Glory of the Winter Garden - Phase 2 - Establishment of a new facility, Racquet Studios, in the Winter Garden. Racquet Studios would be a world class facility for virtual film production, a centre of excellence for skills training in digital and creative arts and a leading virtual film production research and development facility. | TES | March 2023 | N/A - new Business Case | The main risks impacting the ability of the project to proceed are: • Risk of increasing scope and inflation which could impact on the affordability of the project and the ability to deliver the project in accordance with the Business Case. • Risk that future market assumptions, capital costs and revenue streams are not as predicted which may mean that the project is not affordable in the long-term. | Yes - there are remaining barriers to project delivery which may prevent project completion | Planning Consent and Listed Building Consent are required. Applications will be submitted in October 2022, with determination expected in January 2023. | Need greater assurance regarding lead in time for specialist equipment - no scope within delivery programme to manage any delays.
Seven Sisters Country Park Visitor Infrastructure Uplift - the project delivers a comprehensive refresh of the visitor offer at the Country Park, including 233 sqm of new retail space for local businesses and accommodation for the Site Warden. | TES | December 2022 | Yes, but with an adverse impact on the project outputs and outcomes | The main risks impacting the ability of the project to proceed are: • Difficulty in obtaining materials due to COVID-19, supply chain and market demands - mitigated by early identification of materials which might be subject to a long lead-in time. • Listed building consent is required for the Pump Barn in relation to the log burner and 'fitted' furniture fit out - listed building consent application submitted and determination expected in late October 2022. | Yes - there are remaining barriers to project delivery which may prevent project completion | Listed building consent is required in relation to some of the works proposed on the Pump Barn. It is expected that this consent will be received in late October 2022. | Remaining barrier to delivery not reflected in this section of the application but is referenced within the list of risks and has been identified as a barrier by ESCC.
Observer Building, Hastings - the project will support the full redevelopment of the 4,000 sqm Observer Building, which has been empty and increasingly derelict for 35 years, into a highly productive mixed-use building, creating new homes, jobs, enterprise space and support. | TES | September 2023 - full façade renovation | Yes, but with an adverse impact on the project outputs and outcomes | The primary risk continues to be cost uncertainty. Updated costs have been provided for the remaining works but these will probably only be held for a short period of time and therefore may be subject to further increases. | No - there are no remaining barriers to project delivery | There are no remaining barriers to project delivery
Accessing Charleston: Removing the Barrier to Growth (project extension) - establishing a low carbon way for visitors to access Charleston through provision of electric vehicle charging points in the car park and purchase of a electric minibus to convey people to the site from rail and bus stations. | TES | March 2023 | N/A - new Business Case | The main risks impacting the ability of the project to proceed are: • Changes in electric vehicle technology affects the long term viability of the proposed works • Availability of electrical capacity for rapid vehicle charger on site In addition, it has been noted that there are challenges associated with proving the impact of the investment on visitor journeys. | Yes - there are remaining barriers to project delivery which may prevent project completion | Work needs to be undertaken to determine whether there is sufficient electrical capacity on site to facilitate the preferred rapid electrical vehicle charger | Concern regarding lead in time for electric minibus
Sussex Innovation, Falmer - COVID secure adaptions (Hybrid Working Enhancements) - further development on the site to enable more effective hybrid working, including investment in technology (laptops and server upgrade), building enhancements, enhanced hygiene facilities and sustainable transport investment. | TES | March 2023 | N/A - new Business Case | No risks to project delivery have been identified in the Business Case. SELEP concerns regarding lead-in times for some aspects of the project based on updates provided by other projects. The primary risk to the benefits realisation plan is the centres ability to generate enough revenue through attracting additional tenants and for the existing tenants to continue to recruit locally. | No - there are no remaining barriers to project delivery | There are no barriers to project delivery | Concerns as original GBF funded works took significantly longer than expected to deliver. A stated completion date of March 2023, with very limited alternative funding committed, presents a high risk.

## Sheet1 (hidden)
[7 empty] | Cumulative total |  | Revised pipeline |  |  |  | Cumulative total
Band 1 | High Federated Board priority, high deliverability/viability
Band 2 a | High Federated Board priority, medium deliverability/viability | Band 1 | Innovation Park Medway | KMEP2 | 400000 |  | 400000 |  | Band 1 | Innovation Park Medway | KMEP2 | 400000 | 400000
Band 2 b | Lower Federated Board priority, high deliverability/viability |  | Jaywick Market | SE3 | 419060 |  | 819060 |  |  | Broadband extension | SE2 | 477256 | 877256
Band 3 | Lower Federated Board priority, medium deliverability/viability |  | Broadband Extension | SE2 | 477256 |  | 1296316 |  | Band 2a | Thanet Parkway | KMEP1 | 875000 | 1752256
Band 4 | Projects which are not currently in a position to be considered for additional funding | Band 2a | Thanet Parkway | KMEP1 | 875000 |  | 2171316 |  |  | Javelin Way | KMEP3 | 235728 | 1987984
|  |  | Observer Building | TES3 | 315000 |  | 2486316 |  |  | Tindal Square | SE1 | 450000 | 2437984
|  |  | Javelin Way | KMEP3 | 235728 |  | 2722044 |  |  | Observer Building | TES3 | 315000 | 2752984
|  |  | Tindal Square | SE1 | 450000 |  | 3172044 |  |  | Jaywick Market | SE3 | 419060 | 3172044
Existing |  |  | Seven Sisters | TES2 | 84100 |  | 3256144 |  |  | Seven Sisters | TES2 | 84100 | 3256144
| % of GBF committed to date |  | Winter Garden | TES1 | 900000 |  | 4156144 |  | Band 2b
Further prioritsation: | Date of full spend of GBF funding requested |  | LFFN | OSE1 | 500000 |  | 4656144 |  | Band 3 | Discovery Park | KMEP5 | 250000 | 3506144
| % of GBF spend to date | Band 3 | Horizon 120 | SE4 | 907124 |  | 5563268 |  |  | Tendring Bikes | SE5 | 300200 | 3806344
| Added scale of benefits safeguarded |  | Discovery Park | KMEP5 | 250000 |  | 5813268 |  |  | Techfort | KMEP4 | 850000 | 4656344
|  |  | Tendring Bikes | SE5 | 300200 |  | 6113468 |  |  | Horizon 120 | SE4 | 907124 | 5563468
Extensions to BC's | Prioritised by BCR |  | Techfort | KMEP4 | 850000 |  | 6963468 |  | Band 4 | LFFN | OSE1 | 500000 | 6063468
| Date of full spend of GBF funding requested |  | Sussex Innovation | TES4 | 200000 |  | 7163468 |  |  | Winter Garden | TES1 | 900000 | 6963468
| Scale of benefits that will be realised |  | Charleston | TES4 | 321414 |  | 7484882 |  |  | Charleston | TES4 | 321414 | 7284882
[9 empty] | Withdrawn | Sussex Innovation | TES4 | 200000 | 7484882
61356
|  |  | Funding available: | 2527500
|  |  |  | 790000 |  | Balance remaining:
3317500
|  |  | KMEP | 1510728
|  |  | TES | 399100
|  |  | SE | 1346316
|  |  | OSE | 0

## Sheet2 (hidden)
Band | Project | Federated Board priority | GBF ask | Cumulative total | Strengths | Weaknesses/Risks | Conditions attached to prioritisation
Band 1 | Innovation Park Medway | KMEP2 | 400000 | 400000 | • Original GBF funding allocation spent in full • Value Engineering can be applied if required to mitigate cost increases • All required consents in place - assuming no change to materials needed | • Risk of reduced demand for commercial workspace on the site in current economic climate and therefore risk to realisation of project benefits • Risk that if value engineering is employed that materials will no longer meet the requirements of the Design Code attached to the LDO | Outcome of Demand Study to be provided to evidence ongoing demand for the site Written commitment from Medway Council with regard to timely provision of required quarterly reporting on all SELEP funding streams
| Jaywick Market | SE3 | 419060 | 819060 | • Project continues to offer High value for money • Frame for the main building completed • Benefits have increased since the Business Case was submitted • Project is very important to one of the most deprived areas in the SELEP area | • There remains an element of uncertainty regarding the scale of the increase in project costs related to asbestos and ground obstructions • Project will still be delivered to a reduced scope even if additional funding is awarded - potentially reducing benefits • ECC S151 sign off not yet received | ECC S151 sign off needs to be received
| Broadband Extension | SE2 | 477256 | 1296316 | • All planning works (surveys) have already been undertaken and therefore additional costs incurred are confirmed • Project continues to offer Very High Value for Money • Project completion expected in January 2023 (but is this based on September start?) | • Original GBF funding allocation not yet spent in full (extension granted to March 2023) • Risk that the funding will not be drawn down by March 2023, despite the work having been delivered • Programme appears to be based on funding being awarded in September, is the programme still deliverable based on November award? • Question regarding additionality not answered. • ECC S151 sign off not yet received | ECC S151 sign off needs to be received Confirmation required as to the additionality which would be achieved through award of additional funding
Band 2a | Thanet Parkway | KMEP1 | 875000 | 2171316 | • Original GBF funding allocation spent in full • Delivery of the station is nearing completion • Significant additional investment in the project already committed by KCC • Project offers significant benefits to the local area | • Risk of conflicting rail works adversely impacting delivery programme • Limited direct additionality to be achieved through additional GBF funding. Primary additionality appears to relate to securing timely opening of the new station • Uncertainty regarding total cost of level crossing works as detailed design has not yet been completed
| Observer Building | TES3 | 315000 | 2486316 | • Project continues to offer High value for money • Original GBF funding allocation spent in full • Internal works in lower floors completed | • Additional assurance required regarding whether all works being considered for delivery through GBF funding can be capitalised • Risk of further cost increases if remaining works cannot be commissioned quickly. • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received
| Javelin Way | KMEP3 | 235728 | 2722044 | • Original GBF funding allocation spent in full • Project is well progressed with completion expected in December 2022 • The majority of the industrial units are already under offer, which should help to bring forward project benefits | • Value for Money offered by the project is not currently assured. Value for Money was originally demonstrated through calculation of a BCR but now Value for Money exemption appears to be relied on • No firm commitment that the additional GBF funding will be used to improve quality of fit out or return removed elements to project scope. These elements will be re-examined. • There remain outstanding utility works | Value for Money offered by the Project needs to be demonstrated. Project did not originally rely on the Value for Money exemption and a BCR was calculated.
| Tindal Square | SE1 | 450000 | 3172044 | • Original GBF funding allocation spent in full • Project well progressed with completion expected in January 2023 | • No commentary provided with regard to the Value for Money offered by the project. Unable to confirm if project still meets the requirements of VfM exemption 1 • Completion of project is dependent upon utilities works being undertaken, presenting a risk to the delivery programme • ECC S151 sign off not yet received • Unclear which elements of the project scope will be removed if additional funding is not awarded | Provision of explanation as to how Value for Money is being assured and confirmation from ITE that the project continues to meet the requirements of the Value for Money exemption ECC S151 sign off needs to be received
| Seven Sisters | TES2 | 84100 | 3256144 | • Project due to complete in December 2022 (need to confirm if this includes the works to be funded through the additional GBF funding allocation) • Contractor has been appointed and works have commenced onsite | • Listed Building and Planning consent required for elements of the Pump Barn works • No commentary provided with regard to the Value for Money offered by the project. Unable to confirm if the project still meets the requirements of VfM exemption 1 • Original GBF funding allocation not yet spent in full. Extension granted until September 2022 • ESCC S151 sign off not yet received | Provision of evidence that Listed Building Consent and Planning Consent for the Pump Barn works has been secured ESCC S151 sign off needs to be received
Band 3 | Discovery Park | KMEP5 | 250000 | 3506144 | • Project continues to offer High value for money • Project completion currently expected by December 2022 (note risk around lead in times) | • Project has progressed more slowly than originally anticipated. Risk that extended lead in times for specialist lab equipment may result in project delivery extending beyond March 2023
| Tendring Bikes | SE5 | 300200 | 3806344 | • Project helps provide opportunities for more people in a deprived area and there has been significant interest in the bike loan scheme • Additional funding is sought to broaden the groups of people who can benefit from the project • Project due to complete in January 2023 | • Original GBF funding allocation not yet spent in full • Additional funding is in part to deliver works which extend beyond the scope of the original Business Case • BCR offered by the project will potentially be close to 2:1 but additional benefits will be realised which will help offset the increase in cost • ECC S151 sign off not yet received | ECC S151 sign off needs to be received
| Horizon 120 | SE4 | 907124 | 4713468 | • Original GBF funding allocation has been spent in full • GBF project has been delivered • Project continues to offer High value for money | • Project has been delivered as per the scope of the Business Case. Direct additionality appears to relate to works beyond the scope of the original Business Case • No risks in relation to delivery of car park extension enabling works provided and no clear delivery programme • ECC S151 sign off not yet received | ECC S151 sign off needs to be received
| Techfort | KMEP4 | 850000 | 5563468 | • Contractor already onsite delivering existing GBF project so it is expected that works will immediately follow on the new works for which funding is sought • Project offers High value for money | • Construction programme of 4 months stated, with anticipated start date in December 2022. No scope for delay. • Conditions attached to Listed Building and Planning Consent need to be addressed. • Original GBF funding award not yet spent in full (extension granted to December 2022)
Band 4 (not prioritised) | Winter Garden | TES1 | 900000 | 6463468 |  | • Planning Consent and Listed Building Consent have not yet been applied for/received • BCR calculated as 2.04:1. The ITE has raised some queries on the Economic Case and therefore VfM cannot currently be assured • Concerns re robustness of delivery programme - construction period 01/11/2022 to 31/03/2023 but procurement and planning/listed building consent also scheduled for November 2022 • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received
| LFFN | OSE1 | 500000 | 6963468 |  | • No quantification of benefits. Outputs potentially 15km of dark fibre but unclear what this will achieve • No BCR calculated for the project • Thurrock S151 sign off not yet received. ECC S151 sign off may also be required • Greater understanding of Government intervention required to enable award of further funding to Thurrock | Thurrock S151 sign off needs to be received
| Sussex Innovation | TES4 | 200000 | 7163468 |  | • Value for Money exemption 1 applied but there is insufficient information in the Economic Case and in relation to project outcomes for value for money to be assured. Further work needed on all cases of the Business Case. • No risks to project delivery identified in the Business Case. Delivery of the project requires purchase of IT equipment - no consideration appears to have been given to the lead in times for this equipment. Risk to delivery by March 2023. • Greater understanding needed of relationship between the proposed works and the existing GBF works. • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received
| Charleston | TES4 | 321414 | 7484882 |  | • Business Case provided is insufficient to assure that the project offers High value for money. VfM exemption 1 relied upon but insufficient information provided in Economic Case. In addition, further work needed to the financial case • Further work needs to be undertaken to determine whether there is sufficient electrical capacity at the site to power the EV charging points • It is unclear if there are any planning requirements associated with the project • ITE has queried how realistic the stated benefits are • SELEP concerns regarding ability to deliver by March 2023 given extended lead-in times for electric vehicles/associated infrastructure and dependence on utility companies for connection • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received

## Sheet3 (hidden)
Band 1 | Innovation Park Medway | KMEP2 | 400000 | 400000 |  |  |  | Revised pipeline |  |  |  | Cumulative total
| Jaywick Market | SE3 | 419060 | 819060
| Broadband Extension | SE2 | 477256 | 1296316 |  |  | = | Band 1 | Innovation Park Medway | KMEP2 | 400000 | 400000
Band 2a | Thanet Parkway | KMEP1 | 875000 | 2171316 |  |  | Up 1 |  | Broadband extension | SE2 | 477256 | 877256
| Observer Building | TES3 | 315000 | 2486316 |  |  | Up 1 | Band 2a | Thanet Parkway | KMEP1 | 875000 | 1752256
| Javelin Way | KMEP3 | 235728 | 2722044 |  |  | Up 2 |  | Javelin Way | KMEP3 | 235728 | 1987984
| Tindal Square | SE1 | 450000 | 3172044 |  |  | Up 2 |  | Tindal Square | SE1 | 450000 | 2437984
| Seven Sisters | TES2 | 84100 | 3256144 | Remaining balance: | 61356 | Down 1 |  | Observer Building | TES3 | 315000 | 2752984
Band 3 | Discovery Park | KMEP5 | 250000 | 3506144 |  |  |  |  | LFFN | OSE1 | 500000 | 3252984
| Tendring Bikes | SE5 | 300200 | 3806344 |  |  | Down 6 |  | Jaywick Market | SE3 | 419060 | 3672044
| Horizon 120 | SE4 | 907124 | 4713468 |  |  | = |  | Seven Sisters | TES2 | 84100 | 3756144
| Techfort | KMEP4 | 850000 | 5563468 |  |  |  | Band 2b
Band 4 | Winter Garden | TES1 | 900000 | 6463468 |  |  | = | Band 3 | Discovery Park | KMEP5 | 250000 | 4006144
| LFFN | OSE1 | 500000 | 6963468 |  |  | = |  | Tendring Bikes | SE5 | 300200 | 4306344
| Sussex Innovation | TES4 | 200000 | 7163468 |  |  | Up 1 |  | Techfort | KMEP4 | 850000 | 5156344
| Charleston | TES4 | 321414 | 7484882 |  |  | Down 1 |  | Horizon 120 | SE4 | 907124 | 6063468
[8 empty] | Band 4 (not prioritised) | Winter Garden | TES1 | 900000 | 6963468
[9 empty] | Charleston | TES4 | 321414 | 7284882
[8 empty] | Withdrawn | Sussex Innovation | TES4 | 200000 | 7484882

## Sheet4 (hidden)
Band | Project | Federated Board priority | GBF ask | Cumulative total | Strengths | Weaknesses/Risks | Conditions attached to prioritisation
Band 1 | Innovation Park Medway | KMEP2 | 400000 | 400000 | • Original GBF funding allocation spent in full • All required consents in place - assuming no change to materials needed | • Risk of reduced demand for commercial workspace/benefits • Value engineering may mean materials no longer meet the requirements of the IPM Design Code | Provision of Outcome of Demand Study Commitment to timely provision of required quarterly reporting on all SELEP funding streams
| Jaywick Market | SE3 | 419060 | 819060 | • Project continues to offer High value for money • Benefits have increased since the Business Case was submitted | • Uncertainty regarding the scale of the cost increase • Project will still be delivered to a reduced scope even if additional funding is awarded/benefits risk • ECC S151 sign off not yet received | ECC S151 sign off needs to be received 2021/22 year end declarations to be completed (awaiting info from SELEP)
| Broadband Extension | SE2 | 477256 | 1296316 | • All planning works (surveys) have been undertaken so additional costs are confirmed • Project continues to offer V High Value for Money • Project completion expected in January 2023 | • Risk of delayed funding drawdown • Programme appears to be based on funding being awarded in September, is programme still deliverable based on November award? • Question regarding additionality not answered. • ECC S151 sign off not yet received | ECC S151 sign off needs to be received Confirmation required as to the additionality which would be achieved through award of additional funding and confirmation as to programme 2021/22 year end declarations to be completed (awaiting info from SELEP)
Band 2a | Thanet Parkway | KMEP1 | 875000 | 2171316 | • Original GBF funding allocation spent in full • Delivery of the station is nearing completion • Significant additional investment in the project already committed by KCC | • Risk of conflicting rail works adversely impacting delivery programme • Limited direct additionality to be achieved through additional GBF funding (timely opening of station). • Uncertainty regarding total cost of level crossing works as detailed design not yet been completed
| Observer Building | TES3 | 315000 | 2486316 | • Project continues to offer High value for money • Original GBF funding allocation spent in full • Internal works in lower floors completed | • Additional assurance required regarding whether all works being considered for delivery through GBF funding can be capitalised • Risk of further cost increases if remaining works cannot be commissioned quickly. • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received
| Javelin Way | KMEP3 | 235728 | 2722044 | • Original GBF funding allocation spent in full • Project is well progressed with completion expected in December 2022 • The majority of the industrial units are already under offer, which should help to bring forward project benefits | • VfM not currently assured. VfM originally demonstrated through BCR but now VfM exemption appears to be relied on • No firm commitment that the additional GBF funding will be used to improve quality of fit out or return elements to project scope (re-examined) • There remain outstanding utility works | Value for Money offered by the Project needs to be demonstrated. Project did not originally rely on the Value for Money exemption and a BCR was calculated.
| Tindal Square | SE1 | 450000 | 3172044 | • Original GBF funding allocation spent in full • Project well progressed with completion expected in January 2023 | • No commentary provided with regard to the VfM offered by the project. • Completion dependent upon utilities works being undertaken, presenting risk to programme • ECC S151 sign off not yet received • Unclear which elements of the project scope will be removed if additional funding is not awarded | Provision of explanation as to how Value for Money is being assured and confirmation from ITE that the project continues to meet the requirements of the Value for Money exemption ECC S151 sign off needs to be received 2021/22 year end declarations to be completed (awaiting info from SELEP)
| Seven Sisters | TES2 | 84100 | 3256144 | • Project due to complete in December 2022 (need to confirm if this includes the works to be funded through the additional GBF funding allocation) • Contractor has been appointed and works have commenced onsite | • Listed Building and Planning consent required • No commentary provided with regard to the VfM offered by the project. • ESCC S151 sign off not yet received | Provision of explanation as to how VfM is being assured and confirmation from ITE that the project continues to meet requirements of VfM exemption Provision of evidence that Listed Building Consent and Planning Consent for the Pump Barn works has been secured ESCC S151 sign off needs to be received
Band 3 | Discovery Park | KMEP5 | 250000 | 3506144 | • Project continues to offer High value for money • Project completion currently expected by December 2022 (note risk around lead in times) | • Project has progressed more slowly than originally anticipated. Risk that extended lead in times for specialist lab equipment may result in project delivery extending beyond March 2023
| Tendring Bikes | SE5 | 300200 | 3806344 | • Project helps provide opportunities for more people in a deprived area and there has been significant interest in the bike loan scheme • Additional funding is sought to broaden the groups of people who can benefit from the project • Project due to complete in January 2023 | • Additional funding is in part to deliver works which extend beyond scope of the original BC • BCR offered by the project will potentially be close to 2:1 but additional benefits will be realised which will help offset increase in cost • ECC S151 sign off not yet received | ECC S151 sign off needs to be received 2021/22 year end declarations to be completed (awaiting info from SELEP)
| Horizon 120 | SE4 | 907124 | 4713468 | • Original GBF funding allocation has been spent in full • GBF project has been delivered • Project continues to offer High value for money | • Project has been delivered as per the scope of the Business Case. Direct additionality appears to relate to works beyond the scope of the original BC • No risks in relation to delivery of car park extension enabling works provided and no clear delivery programme • ECC S151 sign off not yet received | ECC S151 sign off needs to be received 2021/22 year end declarations to be completed (awaiting info from SELEP)
| Techfort | KMEP4 | 850000 | 5563468 | • Contractor already onsite delivering existing GBF project so it is expected that additional works will immediately follow • Project offers High value for money | • Construction programme of 4 months stated, with anticipated start date in December 2022. No scope for delay. • Conditions attached to Listed Building and Planning Consent need to be addressed.
Band 4 (not prioritised) | Winter Garden | TES1 | 900000 | 6463468 |  | • Planning Consent/Listed Building Consent have not yet been applied for/received • BCR calculated as 2.04:1. ITE has queries on Economic Case and therefore VfM cannot currently be assured • Concerns re robustness of programme - construction period 01/11/2022 to 31/03/2023 but procurement/planning/listed building consent also scheduled for November 2022 • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received
| LFFN | OSE1 | 500000 | 6963468 |  | • No quantification of benefits. Outputs potentially 15km of dark fibre but unclear what this will achieve • No BCR calculated for the project • Thurrock S151 sign off not yet received. ECC S151 sign off may also be required • Greater understanding of Government intervention required to enable award of further funding to Thurrock | Thurrock S151 sign off needs to be received 2021/22 GBF year end declaration to be completed
| Sussex Innovation | TES4 | 200000 | 7163468 | Withdrawn | • VfM exemption 1 applied but insufficient info in the Economic Case and in relation to project outcomes for vfm to be assured. Further work needed on all cases of the Business Case. • No risks to project delivery identified in BC. Delivery requires purchase of IT equipment - no consideration has been given to lead in times. Risk to delivery by March 2023. • Greater understanding needed of relationship between proposed works and existing GBF works. • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received
| Charleston | TES4 | 321414 | 7484882 |  | • BC provided is insufficient to assure that the project offers High vfm. VfM exemption 1 relied upon but insufficient information provided in Economic Case. Further work needed on BC • Currently unknown if there is sufficient electrical capacity at the site to power the EV charging points • Unclear if there are any planning requirements • ITE has queried realism of stated benefits • SELEP concerns regarding ability to deliver by March 2023 given extended lead-in times for electric vehicles/associated infrastructure and dependence on utility companies for connection • ESCC S151 sign off not yet received | ESCC S151 sign off needs to be received

## Sheet5 (hidden)
Band | Project name | Federated Area and Ranking | Existing GBF allocation (£m) | % of GBF allocation spent to date | % of GBF allocation committed to date | Additional GBF requested (£m) | Cumulative total (£m) | GBF spend end date | Strength of case for GBF funding | Impact on project benefits | Estimated Value for Money | Remaining risks | Barriers to project delivery
1 | Innovation Park Medway - Sustainable City of Business | KMEP 2 | 0.77832 | 100% | 100% | 0.4 | 0.4 | 2023-03-01
| Extension of the full-fibre broadband rollout in Essex to reach rural and hard to reach premises | SEB 2 | 1.82 | 15% | 100% | 0.47726 | 0.87726 | 2023-03-01
2a | Tindal Square, Chelmsford | SEB 1 | 0.75 | 100% | 100% | 0.45 | 1.3273 | 2023-03-01
| Thanet Parkway Railway Station | KMEP 1 | 11.999 | 100% | 100% | 0.875 | 2.2023 | 2023-03-01
| Javelin Way development | KMEP 3 | 0.57872 | 100% | 100% | 0.23573 | 2.438 | 2022-12-01
| Observer Building, Hastings | TES 3 | 1.713 | 100% | 100% | 0.315 | 2.753 | 2023-03-01
| Extension of the existing Phase 2 ASELA LFFN project | OSE 1 | 2.5 | 100% | 100% | 0.5 | 3.253 | 2023-03-01 |  | N/A |  |  |  | 0.064516
| Jaywick Market and Commercial Space | SEB 3 | 1.972 | 38% | 100% | 0.41906 | 3.672 | 2023-03-01 | [6 empty] | Note where spend to date figures taken from
| Seven Sisters Country Park Visitor Infrastructure Uplift | TES 2 | 0.2 | 27% | 100% | 0.0841 | 3.7561 | 2023-03-01 | [6 empty] | Quarterly reporting - including actual spend reported for Q2
3 | Discovery Park Incubator | KMEP 5 | 2.5 | 57% | 100% | 0.25 | 4.0061 | 2023-03-01
| Tendring Bikes and Cycle Infrastructure | SEB 5 | 2.3 | 23% | 100% | 0.3002 | 4.3063 | 2023-03-01
| Techfort Phase 2, The Citadel, Dover | KMEP 4 | 1.009 | 0% | 100% | 0.85 | 5.1563 | 2023-03-01 |  | N/A
| Enterprise Centre for Horizon 120 Business and Innovation Park | SEB 4 | 7 | 100% | 100% | 0.90712 | 6.0635 | 2023-03-01
4 | Restoring the Glory of the Winter Garden - Phase 2 | TES 1 | 1.6 | 100% | 100% | 0.9 | 6.9635 | 2023-03-01 |  | N/A
| Accessing Charleston: Removing the Barrier to Growth | TES 4 | 0.32983 | 100% | 100% | 0.32141 | 7.2849 | 2023-03-01 |  | N/A