| Project Change Request |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Section A – Details |  |  |  |  |  |  |  |  |
| Project Name | North Bexhill Access Road |  |  |  |  |  |  |  |
| Lead Officer | Ben Hook |  |  |  |  |  |  |  |
| Lead Authority | East Sussex County Council |  |  |  |  |  |  |  |
| Date Submitted | 22/12/2017 |  |  |  |  |  |  |  |
| Section B – Justification |  |  |  |  |  |  |  |  |
| Description of Change | Increase the LGF allocation for the North Bexhill Access Road Scheme. It is anticipated that the additional costs will be approximately £2m. This £2m will be transferred from the A22/A27 Junction Improvement scheme. |  |  |  |  |  |  |  |
| Reason for Making Change | Additional costs relate to the diversion of utilities, specifically the undergrounding of powerlines and the fibre optic cable have greatly exceeded initial expectations even with value engineering undertaken. Original budget cost estimates were provided by both UK Power Networks (UKPN) and BT Openreach to underground or divert existing lines along the alignment of the new road. When more detailed designs have been undertaken by the utility providers these costs have increased substantially. There have also been a number of unexpected private water and electricity feeds used by local farmers that the developer has had to divert or replace. In August 2017, a large quantity of illegally dumped asbestos was discoverd and the costs for removal have been significant. To mitigate the impact of the road development on nearby residents, additional noise bunds have been included within the design. This has meant significant amounts of earth material have needed to be moved to new locations along the road where mitigation is required. Extensive additional works have also been included within the design to ensure a minimal impact on the local environment, and wildlife and their habitats. The additional cost incurred has meant that the development will meet the highest ecological standards, ensuring conservation of the local area and proliferation of local plant species The reason for using money from the A22/A27 Junction Improvement Scheme: When the round 1 scheme was originally identified Highways England were exploring a series of interventions along this corridor and additional funding was offered up through LGF to ensure these schemes could go ahead. HE have now made their investment announcements for this route and no longer require the additional monies but will still be delivering the previously identified interventions for which this money was allocated. £3m of the £4m is no longer required for investment in this area. As such Team East Sussex have agreed to reallocate to other schemes facing additional costs to achieve the benefits promised within the Growth Deal. |  |  |  |  |  |  |  |
| Alternative Options Considered | Do Nothing – scheme stops construction, failure to capitalise. Seek funds from alternative source – - There are not sufficient funds within the ESCC capital programme to cover any overspend. - Additional borrowing is not an option for ESCC at this time. - This scheme is not compliant with other DfT funding offers and timescales for need not compatible |  |  |  |  |  |  |  |
| Stakeholders Consulted | ESCC – Local Accountable Body Team East Sussex – Local Federated Board Sea Change Sussex – Delivery Partner |  |  |  |  |  |  |  |
| Section C - Impact |  |  |  |  |  |  |  |  |
| Impact on total project cost | Increase £2m |  |  |  |  |  |  |  |
| Impact of LGF allocation | Increase £2m |  |  |  |  |  |  |  |
| Impact of project delivery timescales | Project expected to complete in May 2018 |  |  |  |  |  |  |  |
| Impact on project outputs | NIL |  |  |  |  |  |  |  |
| Impact on project Value for Money | The original business case outlined a BCR of 2.38 based on a full economic appraisal with the stated costs of £16.6m. The increase in the budget to £18.6m means that the new BCR based on the original appraisal method is 2.124. This still sits within the High Value for Money category. With this scheme being so close to completion and the highest risk elements identified and planned for, it also offers much greater certainty of achieving this outcome. |  |  |  |  |  |  |  |
| Impact on SELEP objectives | NIL |  |  |  |  |  |  |  |
| Section D - To be completed by SELEP |  |  |  |  |  |  |  |  |
| LogasNet Number | LGFSE51 |  |  |  |  |  |  |  |
| SELEP Project Number | LGF00085 |  |  |  |  |  |  |  |
| Change Request Number | CCN27 |  |  |  |  |  |  |  |
| Has review of Business Case been completed? | No |  |  |  |  |  |  |  |
| Change agreed with SELEP: | Choose an item. |  |  |  | Date |  |  | Click here to enter a date. |
| Comment | BCR provided in the Business Case was 2.38:1 based on a total project cost of £16.6m. Revised project cost is £18.6m and updated BCR is reported as 2.124:1 which continues to offer High value for money. |  |  |  |  |  |  |  |
| Is Accountability Board approval required? |  |  |  |  |  | Yes |  |  |
| Approved by Accountability Board |  | Approved |  | Date |  |  | 23/02/2018 |  |
| Comment |  | Increase in the LGF allocation approved by Accountability Board. |  |  |  |  |  |  |
| Section E – Government Approval |  |  |  |  |  |  |  |  |
| Date submitted to Government |  |  | Click here to enter a date. |  |  |  |  |  |
| Date agreed by Government |  |  | Click here to enter a date. |  |  |  |  |  |

Guidance

- When is a change request required?

The types of scheme change to be reported include, but are not limited to:

| Financial | - Change to total LGF spend - Change to total cost of a project - Reallocation of LGF |
| --- | --- |
| Scope | - Change to project from original scope as agreed in Outline Business Case submitted to Government for the provisional allocation of Local Growth Fund - Change to project scope from Business Case approved by Accountability Board - Change to intended scheme benefits |
| Outcomes | - Change to the expected outcomes agreed in the project Business Case or as reported to Government through LOGAS net return |

Where LGF funding is being reallocated from one LGF project to another, then two change requests will be required. The first will reduce the LGF allocation to a project and the second will increase the LGF allocation to a project.

If you are unclear whether a change request is required or not please speak to the SELEP Capital Programme Manager.

- Accountability Board approvals

Where a project change includes one or more of the changes listed below, then SELEP Accountability Board approval will be required automatically.

    - Cancellation of a project that is included in the agreed Local Growth Plan;

    - Inclusion of a project not included in the agreed Local Growth Plan;

    - Moving forward of a project previously programmed to start in later years;

    - Delays to project start or end dates of more than six months;

    - Changes to Local Growth Fund project expenditure, or to the agreed core metrics and outcomes, on any single project of more than 10%; or

For other project changes where the SELEP Secretariat or Accountable Body advises that the completion of a change request is required, it will be at the discretion of the SELEP Secretariat to decide whether the change requires Accountability Board approval. SELEP Accountability Board will be made aware of all change requests as part of the LGF update.